## Gantt Chart
GANTT CHART - CS401 Software Eng.
PROJECT TITLE |  | Video Game Rental Service |  |  |  | COMPANY NAME | [6 empty] | VGRentalZ
PROJECT MEMBERS |  | Mazie Xylyn Mauricio / Melinda Kwok / Sitara Meherzad |  |  |  | DATE | [6 empty] | 2020-05-12
WBS NUMBER | TASK TITLE |  | START DATE | DUE DATE | TASK COMPLETE? (Y/N) | PHASE ONE | [9 empty] | PHASE TWO | [29 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [9 empty] | PHASE FIVE | [9 empty] | FINAL PHASE
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK15 |  |  |  |  | WEEK 16
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Select Team Members |  | 2020-01-21 | 2020-02-04 | Y | bar: WEEK 1 M to WEEK 2 F
1.2 | Select Project |  | 2020-01-21 | 2020-02-04 | Y | bar: WEEK 1 M to WEEK 2 F
1.3 | Create Project Docs |  | 2020-01-21 | 2020-02-04 | Y | bar: WEEK 1 M to WEEK 2 F
1.4 | Create Repo |  | 2020-01-21 | 2020-02-04 | Y | bar: WEEK 1 M to WEEK 2 F
1.5 | High Level Abstract |  | 2020-01-21 | 2020-02-04 | Y | bar: WEEK 1 M to WEEK 2 F
2 | Project Definition and Planning
2.1 | UML Project Design |  | 2020-02-07 | 2020-02-21 | Y | bar: WEEK 2 M to WEEK 8 F
2.1.2 | UML Finalization |  | 2020-02-12 | 2020-02-21 | Y | bar: WEEK 2 M to WEEK 8 F
2.2 | Project Requirements Doc |  | 2020-02-07 | 2020-02-21 | Y | bar: WEEK 2 M to WEEK 8 F
2.3 | Gantt Chart |  | 2020-02-07 | 2020-02-21 | Y | bar: WEEK 2 M to WEEK 8 F
2.4 | Roles & Responsibilities Doc |  | 2020-02-07 | 2020-02-21 | Y | bar: WEEK 2 M to WEEK 8 F
2.5 | Finalize All Documentation |  | 2020-03-02 | 2020-03-17 | Y | bar: WEEK 2 M to WEEK 8 F
3 | Project Instantiation
3.1 | Create classes; instantiate objects |  | 2020-03-17 | 2020-04-14 | Y | bar: WEEK 8 M to WEEK 10 F
3.2 | Instantiate appropriate functions |  | 2020-03-17 | 2020-04-14 | Y | bar: WEEK 8 M to WEEK 10 F
3.3 | Instantiate Database |  | 2020-03-17 | 2020-04-14 | Y | bar: WEEK 8 M to WEEK 10 F
3.4 | Simulate objects + data(inventory; customers) |  | 2020-03-17 | 2020-04-14 | Y | bar: WEEK 8 M to WEEK 10 F
4 | Project Instantiation (Part 2)
4.1 | Basic operational front page |  | 2020-04-14 | 2020-04-21 | Y | bar: WEEK 10 M to WEEK 12 F
4.1.2 | Webpage - Login |  | 2020-04-14 | 2020-04-21 | Y | bar: WEEK 10 M to WEEK 12 F
4.1.3 | Webpage - Register |  | 2020-04-14 | 2020-04-21 | Y | bar: WEEK 10 M to WEEK 12 F
4.1.4 | Webpage - Connect to DB |  | 2020-04-14 | 2020-04-21 | Y | bar: WEEK 10 M to WEEK 12 F
5 | Project Instantiation (Part 3)
5.1 | Finish up Classes |  | 2020-04-21 | 2020-04-28 | Y | bar: WEEK 12 M to WEEK 14 F
5.1.2 | Finish up Servlets |  | 2020-04-21 | 2020-04-28 | Y | bar: WEEK 12 M to WEEK 14 F
5.3 | Code integration |  | 2020-04-21 | 2020-04-28 | Y | bar: WEEK 12 M to WEEK 14 F
5.4 | Finish up Website GUI |  | 2020-04-21 | 2020-04-28 | Y | bar: WEEK 12 M to WEEK 14 F
6 | Project Performance + Monitoring
6.2 | Ensure database/website implementation are operational |  | 2020-04-28 | 2020-05-09 | Y | bar: WEEK 14 M to WEEK 16 F
6.3 | Testing for errors |  | 2020-04-28 | 2020-05-09 | Y | bar: WEEK 14 M to WEEK 16 F
6.4 | Testing/Minor touchups |  | 2020-04-28 | 2020-05-09 | Y | bar: WEEK 14 M to WEEK 16 F